## Sheet1
HIGHWAYS | IMPROVEMENT PLAN |  |  | ACTION PLAN
PROJECT NO | DATE | DESCRIPTION | REMEDY | ESTIMATED COST | FUNDING SOURCE | PROGRESS | ORIGIN | Comments | KCC Priority no
2 | 2022-01-01 | Speed Survey ,Dover Road + 20 MPH Zones | As stated | TBA | TBA | on going | V Recas | Speedwatch group formed and are collecting data
3 |  | Traffic island -junc Station Rd and Court Road | TBA | TBA | TBA | TBA | Cllr Byfield | New roadmarkings added
Highway safety for vehicles turning out of
Court rd and from Station Rd
5 | N/A | Double yellow markings Gothic close | TBA | TBA | TBA | TBA | N/A | Amendments to Road appear to have rectified this issue
|  | Parking by vehicles at Gothic close causes traffic | [5 empty] | should this now be removed?
heading to Deal to veer over into middle of road
6 | N/A | 20 mph zones in Walmer | TBA | TBA | TBA | TBA
7 | N/A | Disability access dropped kerbs and tactile surfaces | Addition of dropped kerbs and tactile surfaces | 21000 | HIP | With KCC design | Cllr Eddy/ Murray | Dover Road and The Beach/Kingsdown Road now awaiting consultation.
9 | 2021-11-01 | Cycle path to be extended along Wellington Parade | as stated | N/A | none available | KCC contacted no options provided as way forward | TBA | Question as to how this could be done given private road
10 | 2021-09-01 | Speeding on Dover Road | TBA | TBA | TBA | Removed | TBA | Combined with 2
s | 2022-09-01 | Paving on the strand uneven and a trip hazzard | TBA | TBA | TBA | Completed | Roland | From Resident Mr Henderson (07935262276). Met with Roland May 2022. Only able to action on 12mm drop off or more. All KCC areas of pathway with 12mm actioned. All other interested parties have now actioned their respective responsibilites
14 | 2022-09-01 | works to amend the kerbline and widen the junction of Station Road with Dover Road | TBA | TBA | TBA | TBA | M Eddy | Resident Mr Tasker (<barrington56@gmail.com). Completed and repair work carried out
15 | 2023-06-01 | Cycle Routes - Request to join cycle route 1 to the Skylark trail by adding cycle route along Granville Road | as stated | TBA | HIP | Working with DDC to provide the best solution having spoken to KCC and not agreeing a solution | M Eddy | With DDC awaiting strategy being agreed.
16 | 2023-06-01 | Potholes | Repair work - long term road resurfacing | ongoing | TBA | ongoing | M Eddy | Continous office are reporting these to KCC who are filing as required. Pothole blitz on North Barrack Road this month
17 | 2023-09-01 | Liverpool Road - Outside meadowside centre. Lighting required for safety of residents exiting premsis on foot. No paving is present until Grams Road. | Signage | 0 | KCC | Completed | M Eddy | HIP Priorty met with KCC who are reviewing case and funding | Cleared
18 | 2023-11-01 | Kingsdown Road - Outside of Walmer Castle parking restriction | Parking restrictions | N/A | E Hertiage | English Hertiage looking at weather proofing back up car park to resolve issue | J Murray | DDC and EH have agreed to install double yellow lines along Kingsdown Road
19 | 2024-02-01 | Walking Route | WTC to set up a route and get signage | TBA | KCC/HIP | With M Eddy for route | M Eddy | With Cllr Eddy
20 | 2025-02-01 | Kingsdown Road - Outside of Walmer Castle Crossing the road dange due to blind bend and speed | Additional Signage | TBA | TBA | Design Confirmed |  | With KCC to set a install of "SLOW" painting in the road
21 | 2025-02-01 | Upper Walmer Dover Road -speeding | 20MPH zone not possible as per KCC, Speeds within acceptable limits as per Kent safety partnership. | N/A | TBA | KCC contacted due to current avg speed they would not grant a TRO |  | Letter written to KCC supporting a 20mph zone. Speed survey taken over week in May 2025 results were within acceptable limits for 30mph zone but not low enough to support a 20mph zone.
22 | 2025-06-01 | Upper Walmer Dover Road - Paving | Ask KCC to review | N/A | TBA | KCC contacted no options provided as way forward |  | Stretch of road has been reviewed recently by KCC. Quote from KCC about scope of improvements "However, this is something that can be placed on Walmer Town Council’s Highway Improvement Plan for further discussion but with very little or no scope to widen the footway and there not being sufficient carriageway width to install a pedestrian refuge island, the only possibly feasible form of pedestrian crossing in this vicinity could be a pedestrian dropped kerb, and I am not sure that would be solving the issues being experienced. " Members considered in Sept 2025.
23 | 2025-09-01 | Promenade outside of Adventure Golf - Cycling signage to warn of crossing | Ask KCC to review | 500 | KCC/WTC | Clerk to request through DDC |  | Request with DDC to add signage, updated est cost as no consultation should be required.