## Sheet1
CLIMATE & ECOLOGICAL EMERGENCY ACTION PLAN—COMPILED Spring 2025 part 3 Action May 2025- April 2027
We recognise Natural Solutions to Climate Change include protecting and enhancing carbon-capturing, flood-absorbing, woodlands, grasslands, and wetlands; that community resilience to climate change includes the
protection of food-growing land. Action Plan developed by the Council’s Climate Emergency Working Group.
Recently Completed
Started and ongoing
Agreed at CEWG an proposal to be put together or made to relevant committee
Putting climate mitigation and resilience at the heart of decision making
| Activity | Intended outcome | Led By | Next Steps | Resources required | Time Frame | Comments / contacts
1.1 | Develop new, comprehensive Local Resilience Plan due to expected extreme weather events & lessons learned during pandemic | To be better prepared to help (vulnerable in) community cope with power or broadband outages, shortages, heatwaves, flooding, etc | Clerk / | Template to be developed during and after DDC workshop for level 1 councils (due March/July 2025 but postponed by DDC) | Officer time | After DDC resilience workshop Feb 2026 ? | https://www.kentprepared.org.uk/improving-community-resilience
|  |  | KALC Rep SWG |  | Councillor to attend workshop | Long Term Ongoing
|  |  |  | Link in with Deal Town Council regarding working together on a resilience plan to avoid duplication. |  |  | Implications of Community Governance Review 2026/7
1.2 | Get a new Carbon Audit done in Jan 2027 | Awareness which activities have most emissions GHGases and to show we have achieved WTC net zero without carbon offsetting by 2027. | Officer | To source a carbon audit and quotation. | Officer time | Jan 2027 | Full council provided with update 6 March 2024 on carbon audit impact report of Walmer Parish, after SWG did carbon literacy training Dec 2023.
Territorial 8.45t CO2e
Consumption 15.3t CO2e both per household
1.3 | Liaise with DDC / KALC / NALC about LGReorganisation ; new EK Unitary Authority from 2027. | Find out what extra powers level 1 councils / WTC may have as result of Local Govt reorganisation |  |  |  | Decisions start Jan 2026 | DDC want to unload some car parks, likely only Borrow Pit in Walmer.
(Implications of Community Governance Review 2026/7)
1.4 | Offer training to councillors / officers | Awareness among all members of council & officers |  |  |  |  | Info & Training sessions and information can be found at: https://www.kent.gov.uk/environment-waste-and-planning/climate-change
https://www.carbonfootprint.com/carbonacademy_sbn.html
https://www.cse.org.uk/resources
https://carboncharter.org/events/carbon-literacy-training-3/
Buildings
| Activity | Intended outcome | Led by | Next Steps | Resources required | Time Frame | Comments
2.1 | Get Energy Performance Certificate done on 62 The Strand, publicly owned WTC premises | Find out energy performance of WTC premises, to guide cost effective energy saving plans. | Officer/ Cllr SWG | Renew in 2035 | £210 for EPC | Completed April 2025 | IR Check of No 62, possible installation of curtains.
Score- C (68)
Previous in 2014-E (121)
2.2 | Improve energy efficiency of WTC publicly owned premises with new door. (2.7 refers) | Lower bills, warmer staff, improved energy efficiency so smaller carbon emissions. | Officers | Agreed 5 Nov 2025 Full Council |  | To be completed 31 Jan 2026
2.3 | Leaflet & offer with Energy Saving service with Thermal Imaging Camera service & give aways | Continue to help residents improve energy efficiency of their homes. | Officer | Redesign and confirm new leaflet for IR camera scheme. External Home visits Dec, Jan & Feb | Officer Time | Autumn 2025 & ongoing | DDC offer of give aways, add to leaflet.
2.4 | Get TiC images of Front, rear and side skylights of 62 The strand | To add to the information from EPC and guide decisions on saving energy, guide future decisions | Officer | Take pictures when colder weather comes in | Officer Time | By Dec 25
2.5 | Compare current energy supplier with other suppliers sourced from renewables & low carbon generation. | Enable Council to switch to cost-effective 100% renewable (or at least low carbon) energy supplier | Town Clerk | Renewal in 2027 | N/A | Annually | Done: 2025
2.6 | Seek partner to help us provide rainwater harvesting / butts to residents & community groups where suitable | To recycle rainwater for use in gardens. | Officer | Get information about water harvesting | Officer Time | 2026 | SWG to check with DDC and check Churchill Ave.
2.7 | Install solar panels at office, improve thermal efficiency with alterations to windows and front of office. | Cut energy bills and make WTC premises more energy efficient thereby increasing the resale value of the publicly owned asset in a prudent manner. | All CEWG team of Cllrs & officers | Investigate grants. |  | 2026 /7 | Planning application 22/01443 includes 6 solar roof panels, Extension of rear room, insertion of new rooflight, alterations to shop front including window & door and 2 cycle stands.
2.8 | Collect information about area in Walmer Parish with past experience of flooding or future potential for flooding. |  |  |  |  | 2026 | KRF looking for parish flood wardens.
2.9 | Planning committee to be aware of Advice Kent Fire Service/Resilience Forum, fire breaks needed round developments edge of settlements (wildfires) | ask for safer planning conditions on developments in and around Walmer | Officer / SWG | Advice to be put on planning committee agenda | yearly reminders | Long Term Ongoing
2.1 | Planning cttee to be aware new historic England Advice on energy efficiency & solar on Listed buildings & in Conservation areas | help residents overcome barriers preventing them saving energy | Officer / SWG | Advice to be put on planning committee agenda | reminders when needed | Completed | https://historicengland.org.uk/images-books/publications/adapting-historic-buildings-energy-carbon-efficiency-advice-note-18/heag321-adapting-historic-buildings-energy-carbon-efficiency/
Transport & support for active travel (walking & cycling)
| Activity | Intended outcome | Led by | Next Steps | Resources required | Time Frame | Comments
3.1 | Promote cycle hire from Walmer-based business(es) on our website | To inform the public about cycle hire in the local area | Officer | Put link on our website (like DealTC does) to https://www.hut55.co.uk/bikehire | Officer Time | Near Future | Link has been added to website, The Sustainable page is under construction.
Creation of sustainable travel page.
3.2 | Promote car-sharing platforms and community transport volunteers | Help residents who don’t drive; and help residents drive less. | Officer | On our website. Make poster to put up on community notice boards. | Officer Time | By September 2025 | Poster to be completed
Website Completed
3.3 | Liaise with A&E cttee on making ‘Walking /cycling safer & ‘irresistible’.’ |  | Cllr SWG | Liaise with Walmer road safety and speedwatch groups | Cllr Time | Long Term Ongoing | Gram’s Rd / Station Rd junction likely to be big issue if / when development of Ray’s Bottom arable field goes ahead.
3.4 | Liaise with KCC to install more EV changing spaces for residents without drives | Increase number of EV charging spaces | Officer | Contact KCC regarding places for EV points as well as funding. | Officer Time | Long Term Ongoing | Looking at possibility of adding charge points to top of Court Road, and to upgrade to faster chargers at Rugby club.
3.5 | Speak up for retention of Walmer ticket office & better cheaper train and bus services. | Improvements Walmer side of Walmer Stn e.g. automatic public toilets not in ticket office. | Cllr SWG | Liaise with DealTC (responsible for Ramsgate platform) to improve public toilets & enviro at Walmer stn |  | 2026 | British Toilet Association
Legalise Loos Campaign
3.6 | Explore interest of DDC / DTC in small electric hopper bus to link Walmer residents/ visitors with Boundary Rd, southern Walmer & Deal Castle at weekends | Reduce use of private ICE car in very congested Walmer at weekends. | Cllr SWG | If DDC / DTC / KCC / new UA interested – then see how WTC can support within limits our resources. |  | 2026 | If local business SME/CIC Interested
Speak with Residents association Wellington Parade about possibility; route to be limited to Boundary Rd to Deal Castle to avoid pinch points.
Restoring Nature, enhancing natural carbon capture (including foreshore and coast)
| Activity | Intended outcome | Led by | Next Steps | Resources required | Time Frame | Comments
4.1 | Support / publicise White Cliffs Countryside Partnership – restoring nature work on Foreshore | Encourage Native Species – reduce invasive species. | Officers/Cllrs | Officer to publicise on our website & FB page | Officer time | Long Term Ongoing | Check WCCP website- Contact Alfie
4.2 | Take over management of Churchill Ave Green Space from DDC | Creation community orchard / community garden / biodiversity / peaceful green space for residents young & old | Clerk / Cllr SWG | Continue to liaise with DDC officer Nicola Fairhurst and Ed Craske | Land was offered by DDC at 3 yr lease peppercorn rent July 2023 | 2026 | Hope to have status of space confirmed by end 2025. To consult with volunteers, draft plan, Sept. Start work Nov 2025.
Keep potential volunteers updated.
4.3 | Encourage edible vegetable growing, & rainwater harvesting | To help with community resilience, if / when shortages occur | Clerk | Maintain wildlife friendly category in WIB, proposal to be made to Walmer in Bloom |  | 2026
4.4 | Tree & hedge planting | Explore if KCC offering more plants. DDC interested in short hedge (low-growing labour-saving species) eastern edge of Marke Wood. | Officer | Talk to DDC/KCC about grants. | Officer time | 2026
4.5 |  | Extra carbon capture throughout the parish and residents’ wellbeing. | Officer / Cllr SWG | Agree money for project in Budget |  | 2026 | Young’s Nursery- fruit trees at cost.
£5 donation from those want them.
| Fruit Trees offer for front gardens | [5 empty] | Budget request for 2026/2027 of £880
Sale or Return?
(Ramsgate TC bought at £11 each)
4.6 | Test seawater using services of accredited Laboratory | Provide raw data of findings to complement data obtained by regulator – evidence to push for less pollution of our coastal waters | Officer /Cllr SWG | Place order with laboratory | Officer time; budgeted cost of tests to be done April, July, Sept Oct. (EA do weekly tests May to Sept at Deal pier). | Long Term Ongoing | Action 2025
Review at Jan 2026 meeting, if Swimfo App still shows local sea-bathing water quality as ‘poor’.
4.7 | Work to retain carbon-capturing trees, woodland & grasslands across the parish through planning cttee and WiB / Hawkshill cttee. | Extra carbon capture throughout the parish and residents’ wellbeing. | Officers / Cllrs PF & SWG & WIB Cttee & A&E | Updated management plan Hawkshill Freedown (SC). | Review with DDC tree officer and DDC parks and open spaces as appropriate. | Long Term Ongoing | We advocate for natural solutions to climate change at DAC-KALC and DDC Cl&NForum.
|  | Retain carbon-capturing, flood absorbing trees, woodland & grasslands across the parish through planning cttee and WiB / Hawkshill cttee. |  | Recommendations on planning applications involving TPOs. Apply for new TPOs where possible. |  |  | WTC owned Hawkshill Freedown includes globally rare chalk downland habitat.
WTC Tree policy agreed at full council 6 Nov 2024
4.8 | Set up meeting PAN officer and DDC at DealTC Make all areas mown / managed by DDC in Walmer free of chemical pesticides especially glyphosate. Encourage allotment holders to go pesticide free. | End the use of chemical pesticides on all green areas within Walmer. | On agenda May 2025 DDC C&N Forum | Keep putting the case to DDC Parks and Open Spaces every 6 months. Liaise with other level 1 councils in the district. | Officer and Cllr Time | Meeting with PAN officer 27-11-2025 | Help available from Pesticide action network. pan-uk.org.uk
|  | Also encourage our allotment holders not to use chemical pesticides. To protect both human health and biodiversity. |  |  |  |  | By March 2026 for Allotments
On agenda April 2025 DDC C&NForum
Use contacts website pan-uk.org.uk
Pesticide Action Network & Pesticide Freen Towns - Nick Mole in Dover.
4.9 | Work with Kent Wildlife Trust and DDC to upgrade the protective designation of WTC owned Hawkshill Freedown from LWS (exSNCI) to LNR | Improved protection for carbon-capturing grassland wildlife rich chalk downland in planning law. | WiB cttee and Cllr P Findley | Put forward a proposal to Walmer in Bloom | Up to £330 for KWT officer time |  | What are Community Governance Review implications ?
4.1 | Promote wildlife friendly community gardening through Nature & Biodiversity small grants | Small grants to allow groups to improve biodiversity in the area | Town Clerk | Allow for and authorise small grants for A&E. | No | Long Term Ongoing | Maximum £1500 per year
4.11 | Walmer Peace Garden; wildlife friendly greenspace | Support wildlife friendly community garden and volunteers | WiB cttee |  |  | Ongoing | Volunteers of WPG (project started in 2022) with support of coopted CLLR Sarah Fisher.
Reducing Waste / encouraging recycling/ promoting effective recycling
| Activity | Intended outcome | Led by | Next Steps | Resources required | Time Frame | Comments
5.1 | Offer guidance on recycling facilities in CT14 area |  | Officer | Produce poster / graphic | Officer Time | By Dec 2025
5.2 | WalAPP Walmer Against Plastic Pollution (coincide with 5.6) | Encourage food / drink outlets & hospitality sector to offer zero plastic packaging & alternative to Single use plastic bottles of water. | Cllr SWG | Order stickers for shop / café windows. Cllr SWG to visit, praise actions, enquire their next steps. Show them Refill app. | £60 worth of WalApp non-plastic stickers | Jan / Feb 2026
5.3 | Promote Deal Repair Café in Walmer. A one-off repair café service at Walmer Brocante in August 2026 | Encourage public to re-use, repair instead of buying new | Cllr SWG | Contact Deal Repair Café (or individual fixers); book stall | £10 for non-profit stall (annually, 2026, 2027) | 2026-08-01 | Cllr SWG is a fixer with Deal Repair Café
5.4 | Promote community litter picks, celebrate school litter picks |  | SWG | letters congratulating classes & groups |  | Long Term Ongoing
PDC and DWI beach cleans etc
5.5 | Work with DDC to install water filler close to Sustrans 1 shared cycle / walking path, outside Marine Rd toilets. | Enable residents & visitors to refill personal water bottles 24/7 - discourage single use oil based plastic bottles. | SWG / Officer | Budget agreed July 2023. DDC agreed autumn 2025 (after project on hold while waiting for share of toilet upkeep to be agreed with DDC because sensible installation location is outside toilets). | Officer time. Note: £4000 Allocated in WTC budget for 2 x water fillers since July 2023 | Jan / Feb 2026 | (DDC sent funding application to WTC March 2025, rejected) Toilet maintenance costs agreed Jan 2025.)
5.6 | Continue to reduce use of paper ; encourage councillors to use own (reconditioned) IT tablets, etc. Use QR codes where suitable | To reduce the amount of paper used for office work. | Officer | Office uses recycled paper for agendas and other paperwork | Officer Time |  | It is not sustainable to spend money buying new tablets for councillors.
|  |  |  | Reduction in agendas may be possible. |  |  | Complete switch to QR codes would exclude some members of the community.
Reduction of hard copy agendas has begun, use of recycled paper primarily for all white paper printing. Suitable used paper also used as notepaper.
5.7 | Put up shelf for projector & get projector for cttee room WTC premises | Cttee meeting agendas can be projected onto wall /screen to reduce use of paper & keep meetings focussed | Officer |  | Projector & high shelf | Completed Sep 25 | To note: if we continue to use Walmer PH for full council meetings, secretary of WPH supplies projector for use at WPH.
*See Entry 1.1
Influencing others /Sharing good practice
| Activity | Intended outcome | Led by | Next Steps | Resources required | Time Frame | Comments
6.1 | Work with DDC Climate & Nature Forum sharing good practice. | Learn of initiatives from other TCs / community groups of projects suitable for Walmer; pass on WTC positive experiences. | Cllrs SWG / PF | Clerk discussed TORs Dec 2023. Cllrs attending quarterly from May 2024 |  |  | https://www.dover.gov.uk/Environment/Climate-Change/Dover-Climate-Nature-Change-Forum.aspx
Ongoing
6.2 | WTC stall at DealTC Climate Action Day Nov 2025 | To participate in Deal TC Climate Action Day to inform the public about WTC’s work, | Officer preparation & cllr time RB & SWG |  |  | Completed Nov 2025 | Possible repeat in Nov 2026
6.3 | Support DDC actions to attract providers of CAR CLUBS to district and to CT14 | Help residents avoid cost of private car ownership but access car occasionally |  |  |  | Minuted Oct 2025 at DDC Cl&NF
6.4 | Work with DAC-KALC on resilience, mitigation and adaptation projects |  |  |  |  | Ongoing
6.5 | Support Downs Sailing club especially on NSSR | Support ambition of Downs Sailing Club to run a low carbon National Schools Sailing Regatta in June 2026. | All